PROJECT 2 · DELIVERABLE 6 OF 13

Options Analysis and Recommendation

Three ways WPP Production could use AI to turn one approved campaign into hundreds of market and channel assets

At a glance - Three options were scored on six weighted criteria. Option B, a redesigned workflow with three lanes and four human gates, scores 3.70 out of 5. Option C, platform-led self-service, scores 3.20 and option A, bolt-on AI tools, scores 2.85. - The ranking holds in most tests. B stays first with equal weights and when any single score moves by one point. It loses to C only if speed and cost together carry about 60% of the weight, against 40% in the base case. - Recommendation: build B in stages. Start with a pilot on one campaign, expand only if the pilot shows a clear time and rework gain, and consider limited self-service later for low-risk asset types.

# Executive summary

- The question. How should WPP Production redesign the route from an approved global campaign to market and channel assets, so AI handles repeatable work and people keep the judgement calls?

- The options. A adds AI tools to today’s workflow. B redesigns the workflow around three lanes and four human gates. C moves most production to client self-service on a platform such as WPP Open Pro [7].

- The result. B scores highest at 3.70 out of 5. A scores 2.85 because it speeds up making but leaves about 15 of the 28 working days of review and rework in place (Deliverable 4). C scores 3.20 because it is fastest and cheapest but weakest on brand safety, legal risk and client acceptance.

- How firm this is. The scores are my judgement, not measurements. The lead over C is clear in the base case and disappears if speed and cost are given much more weight than quality and risk. Deliverable 8 tests the numbers behind the speed and cost scores.

- What to do. Run B as a staged pilot on one live campaign wave, with clear stop rules, and keep C as a later, limited extension.

# The three options

| Option | What it is | What changes | Main trade-off |
| --- | --- | --- | --- |
| A. Bolt-on AI tools | Production teams use generative AI for resizing, translation, image variants and checks, inside today’s workflow. Review stays as it is: every finished asset, one stage after another. | Very little. Same steps, same reviewers, same client rounds. | Cheapest to start. Does not touch the 15 review and rework days, so the timeline barely moves. |
| B. Three lanes, four gates | Work is sorted into three lanes (Deliverable 5). AI does the repeatable work in Lane 1 under agreed rules, AI drafts and people finish in Lane 2, and people decide in Lane 3. Four human gates replace repeated review of every asset. | Review moves earlier and becomes selective: approve the rules and a first sample, check every high-risk item, sample the rest. | Largest potential gain in time and rework. Needs clients to accept sampling and needs new working habits. |
| C. Platform-led self-service | Clients, or WPP on their behalf, generate market and channel versions through a self-service platform such as WPP Open Pro [7]. People handle exceptions only. | Most of the production workflow. The agency role moves from making assets to running the platform and handling exceptions. | Lowest cost per asset if it works. Brand safety, legal risk and client accountability move to the client or the platform. |

All three use AI. The difference is where people stay involved and how review is organised. Option B is the working hypothesis from the start of the project: the main gain comes from fewer review loops, not faster generation. This analysis tests it against two alternatives.

# How the options were scored

## Criteria and weights

| Criterion | Weight | Why it matters here |
| --- | --- | --- |
| Quality and brand safety | 25% | Wrong or off-brand work reaches the public. This is the main promise to clients, and 96% of marketers say human oversight is critical [9]. |
| Speed | 20% | Elapsed time from approved master to delivered assets. Speed to market is one of the clearest client benefits. |
| Cost per asset | 20% | Hands-on cost of making and reviewing one asset. WPP plans £500m of annual savings by 2028 [10]. |
| Legal and IP risk | 15% | Claims, rights, copyright and disclosure. Agency leaders name accuracy and bias (63%) and legal risk (62%) as the main barriers to AI use [8]. |
| Client acceptance and revenue protection | 10% | Whether clients will accept the new way of working, and whether fee income is protected. Analysts see AI tools as a threat to agency revenue [5][13]. |
| Change and people impact | 10% | Disruption to roles, skills and morale. WPP says WPP Production is not driven by cost cutting and does not anticipate layoffs [11]. |

The weights are my judgement. Quality and risk together carry 40%, speed and cost together 40%, and client and people effects 20%. A reviewer at WPP or a client might weight them differently, which is why the sensitivity tests below matter.

## Scores

Each option is scored from 1 (poor) to 5 (strong) on each criterion, where a higher score is always better. For cost, a score of 5 means the lowest cost per asset. For change and people impact, a score of 5 means the least disruption.

| Criterion | Weight | A. Bolt-on | B. Three lanes | C. Platform |
| --- | --- | --- | --- | --- |
| Quality and brand safety | 25% | 3 | 4 | 2 |
| Speed | 20% | 2 | 4 | 5 |
| Cost per asset | 20% | 3 | 4 | 5 |
| Legal and IP risk | 15% | 2 | 4 | 2 |
| Client acceptance and revenue protection | 10% | 4 | 3 | 2 |
| Change and people impact | 10% | 4 | 2 | 2 |
| Weighted score (out of 5) | 100% | 2.85 | 3.70 | 3.20 |

## Reasons for the scores

| Criterion | A. Bolt-on AI tools | B. Three lanes, four gates | C. Platform-led |
| --- | --- | --- | --- |
| Quality and brand safety | Unchanged review, but AI used with no shared rules can add inconsistent output. 3 | Rules are agreed first, humans decide the risky items, and checks are logged. 4 | Quality depends on client skill and platform controls, and the risk of sameness rises [9]. 2 |
| Speed | Only the making steps get faster. About 15 of 28 days stay. 2 | Fewer, earlier review loops. Design target 18 days against 28 (Deliverable 7). 4 | Fastest, because most waiting disappears. 5 |
| Cost per asset | Saves part of the Lane 1 and Lane 2 hours, with rework unchanged. 3 | Saves hours in Lanes 1 and 2 and cuts rework, but adds gate and sampling work. 4 | Lowest hours per asset once set up. 5 |
| Legal and IP risk | Individuals choose their own tools and prompts, so exposure is uneven [8]. 2 | Every claim, rights and sensitive-market item is checked by a person at Gate 3. 4 | Provenance and claims checks move to the client. 2 |
| Client acceptance and revenue protection | No change for clients. Fee pressure from AI remains [5]. 4 | Clients must accept pattern approval and sampling, which is a real change. 3 | Fits smaller brands only, may cut agency fees, and WPP presents it as complementary [7]. 2 |
| Change and people impact | Small change to how people work. 4 | New roles for gate owners and a different workload for reviewers. 2 | Largest change to production roles, though WPP expects no layoffs [11]. 2 |

Evidence is thin on all six criteria. WPP publishes no volumes, times or savings for WPP Production [11][12], and the survey evidence is from US vendors and trade bodies [8][9]. The scores therefore rest on reasoning about how each option changes the map in Deliverable 4.

# How sensitive is the ranking?

Figure 1. Weighted scores out of 5 under three sets of weights. The highest score in each group is in bold.

| Test | A | B | C | Result |
| --- | --- | --- | --- | --- |
| Base weights | 2.85 | 3.70 | 3.20 | B first |
| Equal weights (one sixth each) | 3.00 | 3.50 | 3.00 | B first |
| Safety first (quality 35, legal 25, others 10) | 2.85 | 3.70 | 2.60 | B first, by a wider margin |
| Speed and cost first (30 each, others 10) | 2.80 | 3.70 | 3.80 | C narrowly first |
| Any single score moved up or down by 1 | – | – | – | B stays first in all cases tested |
| B’s client-acceptance score cut to 2 and people score to 1 | 2.85 | 3.50 | 3.20 | B first |
| B’s quality and legal scores both cut to 3 | 2.85 | 3.30 | 3.20 | B first, narrowly (3.30 against 3.20) |

- B’s lead is robust to the weights, with one exception. If speed and cost together carry about 60% of the weight (40% in the base case), C overtakes B. A board that cares mostly about speed and unit cost would reasonably prefer C.

- A is never first in any test run. It scores only 2 on speed and 2 on legal risk, because it leaves the review structure and the AI rules unchanged.

- B’s weak points are people and clients. Its lowest scores are on change impact and client acceptance. The pilot should test both, not just time saved.

What would change this advice - If a pilot shows review is a much smaller share of elapsed time than the 54% assumed (Deliverable 4), B’s speed advantage over A shrinks. - If large clients refuse pattern approval and sampling, B reduces to A with better rules. - If clients adopt platform tools quickly and accept the quality risk, C becomes more attractive for low-risk asset types.

# Stakeholders

Figure 2. Stakeholders by influence and interest. Positions are my judgement from public information, not survey results.

| Stakeholder | Wants | Likely concern | How to engage |
| --- | --- | --- | --- |
| Client brand teams | Faster delivery, consistent brand, no surprises | Loss of control if they approve samples rather than every asset | Co-design the rules at Gate 1; show sample results early |
| Client legal and procurement | Clear accountability for claims and rights; lower cost | AI-made content with unclear origin | Agree the AI-use rules and who signs off claims |
| WPP Production leadership | Cost and speed gains within Elevate28 [10][11] | Disruption to clients while the unit is still being formed | Sponsor the pilot; own the targets |
| WPP creative leads | Creative integrity across versions | Idea diluted by automated versions | Own Gate 2; set what can and cannot change |
| Brand and legal reviewers | Fewer, better-prepared reviews | Being blamed for errors in items they only sampled | Define sample sizes and escalation rules with them |
| Local market teams | Respect for local judgement | Being bypassed by machine translation | Keep cultural review in Lane 3 with named owners |
| Production artists and producers | Less repetitive work; skills growth | Job security and deskilling | Involve in pattern design; train on tools and rules |
| WPP Open and HEX technologists | Real use of the platform and tools [1] | Pressure to deliver tools before rules exist | Build tools to the gate rules, not ahead of them |
| Platform providers (Google, Meta) | Wider use of their creative tools [5][6][14] | Not a direct party, but shapes what clients expect | Monitor; keep the design able to use their tools |
| WPP group leadership and investors | Savings and a credible AI story [3][10] | Slow proof; reputational risk from AI errors | Report pilot results against stated targets |

Production artists, producers and local teams have the least formal influence but carry the day-to-day change. The pilot design should involve them from the start, because a gate that people do not trust will be bypassed.

# Recommendation

Recommended option Option B: redesign the workflow around three lanes and four human gates, and introduce it in stages with stop rules. Take the quick wins from A inside that design, and consider C only for low-risk asset types once B has proved itself.

| Stage | When | What happens |
| --- | --- | --- |
| 0. Prepare | Weeks 0 to 4 | Choose one pilot campaign wave. Write the brand and AI-use rules as checkable rules. Record today’s time, hours and rework as the baseline. |
| 1. Pilot | Weeks 5 to 16 | Run the three lanes and four gates on that wave. Measure elapsed time, hands-on hours, assets sent back and critical errors. |
| 2. Extend | Months 4 to 8 | Move to three to five clients if the pilot meets its targets. Add gate owners and train reviewers. |
| 3. Scale and review | Months 9 to 12 | Make B the standard route. Test self-service for low-risk Lane 1 asset types, in the spirit of option C. |

- Proposed pilot test (my assumption): continue only if elapsed time is at least 25% shorter than the baseline and assets sent back for brand or legal reasons do not rise. Deliverable 9 sets the full stop rules.

- Why not start with C? It carries the most risk on the criteria that clients care about most, rests on the least reliable evidence [7], and needs B’s rules and gates to work safely anyway.

- Why not stop at A? It is a sound first step but leaves the largest delay, review and rework, untouched.

# Limitations

- Scores and weights are my judgement. They have not been tested with WPP staff or clients. The sensitivity tests show which conclusions are firm.

- Public evidence is thin. WPP does not publish production volumes, times or savings, and the unattributed claim of “up to 70%” faster content production [6] is used only as an optimistic case in Deliverable 8.

- The options are simplified. A real design would mix elements, and the options would be refined with client input.

# Key terms in plain English

| Term | What it means |
| --- | --- |
| Weighted decision matrix | A table that scores options on several criteria and multiplies each score by how much that criterion matters. |
| Sensitivity test | Changing an assumption to see whether the conclusion still holds. |
| Gate | A point in the workflow where a named person must approve before work continues. |
| Sampling | Checking a small share of items instead of all of them, with a rule for checking more if errors appear. |
| Self-service platform | A tool that lets the client create and publish assets directly, with little or no agency involvement. |
| Stop rule | A pre-agreed result that ends or rescopes a pilot. |

# Sources

Numbers in square brackets match this list and the Source Log (Deliverable 1).

| Ref | Source (select the title to open it) |
| --- | --- |
| [1] | WPP 2026 Interim Results. WPP (RNS via Investegate), Aug 2026. |
| [3] | WPP Is “On Track” With Turnaround Plan, as Revenue Drops 5.6% in First Half of 2026. Adweek, Aug 2026. |
| [5] | WPP’s rocky Q4 underscores AI disruption across agencies. eMarketer, 2026. |
| [6] | WPP bets on $400 million Google AI alliance. Campaign Asia, 2025 (date not shown). |
| [7] | WPP’s AI Tool Lets Brands Skip Agencies for Ad Creation. WebProNews, Undated. |
| [8] | The State of AI Inside US Marketing Agencies 2026 (reported by MediaPost). MediaPost, 6 Jul 2026. |
| [9] | AI speeds up content production but sameness a problem (CMOtech UK). CMOtech UK, 18 Mar 2026. |
| [10] | Strategy Update and 2025 Preliminary Results. WPP (RNS via Investegate), 26 Feb 2026. |
| [11] | Why WPP is rebuilding its production model for always-on marketing. eMarketer, 30 Jan 2026. |
| [12] | WPP unifies 10,000 creatives into a single global content factory for the AI era. Mediaweek (Australia), 23 Jan 2026. |
| [13] | FAQ on ad agencies: Consolidation, AI disruption, and what’s changing in 2026. eMarketer, 2026. |
| [14] | Meta Plans To Automate All Ad Creation By 2026: Report. MediaPost, 2 Jun 2025. |